SHILABS

# AI Sales Engine

Concurrent Development Plan

Implementation workstreams, dependencies, milestones and realistic timeline for an in-house build

Version 2.0 | September 2026

|  | Planning assumption This plan assumes one primary developer using Codex heavily. Independent workstreams are designed to run concurrently where possible, but integration gates, QA and external API access still control the final timeline. |
| --- | --- |

# 1. Development Strategy

Build a modular monolith API plus a separate background worker. Avoid premature microservices. Frontend, platform foundation and AI contracts can start together; integrations should begin only after stable domain interfaces exist.

PRODUCT / UX PLATFORM CORE AI FOUNDATION │ │ │ Wireframes Repo / DB / Auth AIProvider Screen states CRM domain schemas/prompts Acceptance rules Audit / events test harness └──────────────┬──────────────────────┘ ↓ CONVERSATIONS + AUTOMATION ↓ WHATSAPP + MEETINGS + DASHBOARD ↓ HARDENING + UAT

# 2. Concurrent Workstreams

| Workstream | Primary deliverables | Depends on | Parallel with |
| --- | --- | --- | --- |
| A. Product / UX | Wireframes, states, API/UI contracts, acceptance criteria | Approved product flow | B, C |
| B. Platform Core | Repo, config, PostgreSQL, auth/RBAC, audit foundation | Architecture | A, C |
| C. AI Foundation | AIProvider abstraction, structured schemas, prompt contracts, simulator | Architecture | A, B |
| D. CRM Domain | Companies, contacts, leads, deals, pipeline, activity | DB/auth base | C, E |
| E. Messaging | Conversation/message models, internal simulator, realtime UI | DB/auth | D, C |
| F. Automation | Events, Redis, BullMQ, follow-up rules, cancellation/retries | Event contracts | D, E |
| G. Integrations | WhatsApp, email, optional calendar adapters | Stable domain interfaces | Admin UI |
| H. Dashboard / Analytics | KPIs, hot/at-risk rules, aggregations | Real CRM contracts/data | G |
| I. Hardening | E2E, security, observability, deployment | Integrated MVP | UI polish |

# 3. Technology Plan

| Layer | Recommendation |
| --- | --- |
| Frontend | React + TypeScript + Vite |
| Backend | Node.js + TypeScript + Express/Fastify |
| Database | PostgreSQL |
| ORM | Prisma |
| Queue/cache | Redis + BullMQ |
| Realtime | Socket.IO / WebSocket |
| AI | OpenAI behind internal AIProvider |
| RAG | PostgreSQL + pgvector initially |
| Testing | Vitest/Jest + Supertest + Playwright |
| Deployment | Dockerized web/api/worker services |

# 4. Milestones

| Milestone | Scope | Acceptance criterion |
| --- | --- | --- |
| M1 Foundation | Repo, env, DB, migrations, auth, roles, health checks, tests | Local platform runs cleanly |
| M2 CRM | Companies, contacts, leads, deals, pipeline, activities | Lead lifecycle works without AI |
| M3 Conversation + AI Qualification | Internal chat, AI provider, qualification, scoring, knowledge v1 | Conversation can update structured lead qualification |
| M4 Automation | Events, BullMQ, follow-up rules, retries/cancellation | Durable no-response follow-up works |
| M5 WhatsApp | Webhook, dedupe, outbound, delivery status, human takeover | End-to-end WhatsApp flow works |
| M6 Meetings | Availability, booking, reschedule/cancel, timezone handling | Qualified lead can book safely |
| M7 Dashboard | KPIs, due follow-ups, hot/at-risk rules, notifications | Native operational dashboard uses real data |
| M8 Release | E2E, security, provider failures, deploy/UAT | Pilot-ready MVP |

# 5. Tentative Timeline — One Primary Developer + Codex

| Week | Concurrent focus | Exit milestone |
| --- | --- | --- |
| 1 | Architecture freeze, repo scaffold, UI shell, DB schema, AI contracts | Project runs locally |
| 2 | Auth/RBAC, users, company/contact/lead CRUD, Leads UI | Core CRM records work |
| 3 | Deals, pipeline, activity, internal conversation models/simulator | Lead lifecycle + chat simulation |
| 4 | AI SDR, qualification extraction, deterministic score, knowledge v1 | AI qualification demonstrable |
| 5 | Redis/BullMQ, events, automation rules, follow-up queue, audit | Durable follow-up without WhatsApp |
| 6 | WhatsApp adapter/webhooks, delivery state, human takeover, realtime inbox | WhatsApp end-to-end |
| 7 | Internal availability/booking, meeting UI/APIs, optional calendar sync | Meeting booking works |
| 8 | Dashboard metrics, hot/at-risk rules, notifications, integration health | Operational MVP complete |
| 9 | E2E tests, edge cases, security pass, UX cleanup | Release candidate |
| 10 | Deployment, pilot data, stakeholder UAT fixes | Pilot-ready |
| 11-12 | Stabilization / production issues / requirement-change buffer | Stable MVP |

|  | Broader v1 Research enrichment, outbound campaigns, Lead Hunter and advanced AI Sales Manager capabilities should be planned as a separate 4–6 week extension after the core MVP, depending on scope and external data requirements. |
| --- | --- |

# 6. Codex Task Order

| Task | Codex scope |
| --- | --- |
| 1 | Scaffold only: monorepo, configs, Docker dev services, READMEs |
| 2 | Prisma schema, migrations, seed strategy |
| 3 | Auth/RBAC/users |
| 4 | Companies/contacts/leads CRUD |
| 5 | Deals/pipeline/activity/audit |
| 6 | Conversation/message simulator + realtime |
| 7 | AI provider + qualification + scoring + knowledge |
| 8 | Events + Redis/BullMQ + follow-up automation |
| 9 | WhatsApp integration + human takeover |
| 10 | Meetings + optional calendar adapter |
| 11 | Dashboard/analytics/notifications |
| 12 | E2E, security, deployment |

# 7. Important Engineering Gates

Do not connect WhatsApp before internal conversation flow works.

Do not build dashboard logic from mocked numbers; use real CRM queries.

Do not use in-memory timers for follow-up.

Do not let AI calculate or persist authoritative business state without server validation.

Do not let feature modules call provider SDKs directly; use adapters/interfaces.

Review Codex diff after every milestone before giving the next task.

Run type-check, lint and tests after every bounded Codex task.

# 8. Primary Risks and Controls

| Risk | Control |
| --- | --- |
| AI sends unsafe/incorrect claim | Approved knowledge + prompt policy + human escalation |
| Duplicate WhatsApp webhook | Provider-message idempotency + DB unique constraint |
| AI sends after human takeover | Check conversation mode before enqueue and immediately before send |
| Pending follow-up fires after reply | Cancel pending job + worker eligibility re-check |
| Double meeting booking | Transactional reservation / uniqueness constraints |
| Provider outage | Retries, failure state, notification, no duplicate sends |
| Codex architecture drift | Master plan + module boundaries + milestone-gated prompts |

# 9. What to Show the Stakeholder

For approval, communicate that the core product is in-house, development is broken into parallel workstreams, MVP is targeted in approximately 10 weeks with 2 weeks stabilization buffer, and advanced research/outbound/forecasting remain a separate extension rather than blocking the first operational release.